## backlog and story point
Backlog Task ID | Story | Assigned to | Status | Original | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint
UserStory 1: landing page | 1 |  |  | 3 | [5 empty] | 3.5
Backend Development |  | Krishika Khadka | Done |  | 0 | 0 | 1 | 1.5 | 0 | 2.5
Frontend Development |  | Krishika Khadka | Done |  | 0 | 0 | 0 | 0 | 0.5 | 0.5
Testing |  | Krishika Khadka | Done |  | 0 | 0 | 0 | 0 | 0.5 | 0.5
UserStory 2: Login | 1 |  |  | 3 | [5 empty] | 3.5
Backend Development |  | Ashish k.Shrestha | Done |  | 0 | 0 | 0 | 0 | 2 | 2
Frontend Development |  | Ashish k.Shrestha | Done |  | 0 | 0 | 0 | 1 | 0 | 1
Testing |  | Ashish k.Shrestha | Done |  | 0 | 0 | 0 | 0 | 0.5 | 0.5
UserStory 3: Registration Page | 1 |  |  | 3 | [5 empty] | 3.5
Backend Development |  | Prajwal Pokhrel | Done |  | 0 | 1 | 0.5 | 0 | 0 | 1.5
Frontend Development |  | Prajwal Pokhrel | Done |  | 0 | 0.5 | 1 | 0.5 | 0.5 | 1.5
Testing |  | Prajwal Pokhrel | Done |  | 0 | 0 | 0 | 0.5 | 0 | 0.5
UserStory 4: Dashboard | 1 |  |  | 3 | [5 empty] | 2.5
Backend Development |  | Prajwal Pokhrel | done |  | 0 | 0 | 0 | 0 | 1 | 1
Frontend Development |  | Hasina KC Khatri | Done |  | 1 | 0 | 0 | 0 | 0 | 1
Testing |  | Hasina KC Khatri | Done |  | 0 | 0 | 0 | 0 | 0.5 | 0.5
UserStory 5: Add mvoies | 1 |  |  | 3 | [5 empty] | 4
Backend Development |  | Hasina KC khatri | done |  | 1 | 0 |  | 0.5 | 1 | 2.5
Frontend Development |  | Ashish k.shrestha | Done |  | 0 | 1 | 0 | 0 | 0 | 1
Testing |  | Hasina KC khatri | Done |  | 0 | 0 | 0 | 0 | 0.5 | 0.5
UserStory 5: Available movies | 1 |  |  | 3 | [5 empty] | 3.5
Backend Development |  | Prajwal Pokhrel ,Ashish k | done |  | 0 | 0 | 0.5 | 1 | 0.5 | 2
Frontend Development |  | Prajwal Pokhrel | Done |  | 0 | 0.5 | 0 | 0 | 0 | 0.5
Testing |  | Prajwal Pokhrel | Done |  | 0 | 0 | 0 | 0 | 1 | 1
UserStory 6: Customer page | 1 |  |  | 3 | [5 empty] | 5
Backend Development |  | Hasina kC | Done |  | 0 | 0 | 0.5 | 1 | 1 | 3.5
Frontend Development |  | Hasina kC | Done |  | 0 | 0 | 0.5 |  | 0 | 0.5
Testing |  | Hasina kC | Done |  | 0 | 0 | 0 | 0 | 1 | 1
UserStory 7: EDIT SCREENING PAGE | 1 |  |  | 3 | [5 empty] | 3.5
Backend Development |  | Ashish K.S | Done |  | 0 | 0 | 0.5 | 0.5 | 1 | 2
Frontend Development |  | Krishika khadka | Done |  | 0 | 0.5 | 0 | 0 | 0 | 0.5
Testing |  | Ashish K.S | Done |  | 0 | 0 | 0 | 0 | 1 | 1
UserStory 8: ADMIN PROFILE | 1 |  |  | 3 | [5 empty] | 3.5
Backend Development |  | Hasina kC | Done |  | 0 | 1 | 0.5 | 0.5 | 0 | 2
Frontend Development |  | Hasina kC | Done |  | 0 | 0 | 0.5 | 0.5 | 0 | 1
Testing |  | Hasina kC | Done |  | 0 | 0 | 0 | 0 | 0.5 | 0.5
|  |  |  | TOTAL : | 1 | 3.5 | 5.5 | 5.5 | 13 | 28.5

## Sheet2
SPRINT 1
FEATURES/PAGE | day 0 | day 1 | day 2 | day 3 | day 4 | day 5
Registration page | 1 | 0.5 |  | 1 | 1
Login page | 3 |  | 0.5 | 1 | 1 | 1
landing page | 2 | 0.5 |  | 1 | 1 | 0
dashboard | 3 | 1 | 1 | 1 |  | 0
remaining | 9 | 7 | 5.5 | 1.5 | -1.5 | -2.5
ideal trend | 9 | 7.2 | 5.4 | 3.6 | 1.8 | 0
SPRINT 2
FEATURES/PAGE | day 0 | day 1 | day 2 | day 3 | day 4 | day 5
ADD MOVIES | 3 | 0.5 |  | 1 | 1
RESET PASSWORD | 2 |  | 0.5 | 0.5 | 0.5 | 0.5
AVMV FRAME | 1 | 0.5 | 0.5 | 0 | 0 | 0
PURCHASE TICKET | 2 | 1 | 1 | 0.5 | 0.5 | 0
remaining | 8 | 6 | 4 | 2 | 0 | -0.5
ideal trend | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 0
SPRINT 3
FEATURES/PAGE | day 0 | day 1 | day 2 | day 3 | day 4 | day 5
ADD MOVIES PAGE | 3 | 0.5 | 0.5 | 1 | 1
IMPORT MV IMG | 3 | 0.5 | 0.5 | 1 | 1 | 0
SHOW RECIEPT/BUY | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.5
UPADTE/ | 2 | 0 | 0 | 0.5 | 0.5 | 1
remaining | 10 | 8.5 | 7 | 4.5 | 1.5 | 0
ideal trend | 10 | 8 | 6 | 4 | 2 | 0
SPRINT 4
FEATURES/PAGE | day 0 | day 1 | day 2 | day 3 | day 4 | day 5
DELETE MV/update | 3 | 0.5 | 0.5 | 1 | 1
ENHANCEMENTS | 3 | 0.5 | 0.5 | 1 | 1 | 0
SHOW SALES/TICKET SOLD | 3 | 0.5 | 0.5 | 0 | 0.5 | 1
EDIT SCR FRAME | 2 | 0 | 0 | 0.5 | 0.5 | 1
remaining | 11 | 9.5 | 8 | 5.5 | 2.5 | 0.5
ideal trend | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0
SPRINT 5
FEATURES/PAGE | day 0 | day 1 | day 2 | day 3 | day 4 | day 5
GENERATE TICKETS | 1 | 0 | 1 | 0 | 0 | 0
PROFILE DATA CHARTS | 3 | 1 | 0.5 | 1 | 1 | 0
ADMIN PROFILE | 2 | 0 | 0 | 0 | 1 | 0.5
MVC | 6 | 1 | 1 | 1.5 | 1.5 | 1
remaining | 12 | 10 | 7.5 | 5 | 1.5 | 0
ideal trend | 12 | 9.6 | 7.2 | 4.8 | 2.4 | 0